## Sheet1
| Tasks | start date | Actual Start date | expected end date | Actual End date
Project Setup and Database Design
| Set up the project structure. | 2024-07-08 | 2024-07-08 | 2024-10-08 | 13/8/2024
Design the MongoDB schema for both primary and secondary data.
Define relationships between primary farmer details and secondary data (land details, documents).
Frontend Development (Form Components) |  | 2024-11-08 | 14/8/2024 | 15/8/2024 | 16/8/2024
Homepage
Login and register
Multi-Step Form Structure
FarmerDetailsForm:
AddressDetailsForm:
LandDetailsForm :
| File Upload Integration (Document Upload Form) |  | 26/8/2024 |  | 28/8/2024
Backend Development (API and Database Integration) |  | 16/8/2024 | 20/8/2024 | 20/8/2024 | 28/8/2024
Set up the Node.js server with Express.
Develop API routes for handling farmer data and documents.
Implement validation for Aadhar/Voter ID and Farmer ID generation.
OTP Verification (Twilio Integration) |  | 21/8/2024 | 2024-03-09 | 24/8/2024 | 2024-04-09
Implement OTP verification as the first step in the multi-step form.
Finalizing Multi-Step Form (Linking Frontend and Backend) |  | 25/8/2024 | 2024-05-09 | 30/8/2024 | 2024-07-09
Complete form submission logic to send data to the primary and secondary databases.
Link land details and documents to the secondary database with the generated Farmer ID.
Adding validations in the frontend and Backend side |  | 2024-01-09 | 2024-08-09 | 2024-04-09
Farmer Dashboard- Frontend development (React and React-Bootstrap) |  | 2024-05-09 |  | 2024-09-09
Farmer's Portal
Application for planting
check weather
Plant protection
Agro Advisory
make a call